## Acceptance tests
UAT and acceptance tests
Agree severity and sign-off gates before testing. A pass requires observed evidence and an accountable reviewer. Source: B13.
Test ID | Requirement ID | Scenario | Preparation | Expected result | Actual result | Evidence reference | Result | Tester and date | Defect ID
UAT01 | OPS02 | Create a vessel call and submit an allocation request. | Use a representative call and requester account. | Request retains call identity, requester and permitted next state. |  |  | Not run
UAT02 | OPS01 | Amend requested position after allocation approval. | Maintain requested, approved and observed values. | All three facts remain distinct with history. |  |  | Not run
UAT03 | OPS04 | Attempt simultaneous conflicting approvals. | Use two authorized operator accounts. | Conflict is controlled and the final approved state is unambiguous. |  |  | Not run
UAT04 | OPS05 | Apply a permitted queue override. | Use mixed priorities and an authorized supervisor. | Reason, actor and changed priority are recorded. |  |  | Not run
UAT05 | OPS03 | Submit a request violating an approved constraint. | Choose a port-approved rule and version. | The request is rejected or held with an explanation. |  |  | Not run
UAT06 | INT06 | Replay duplicate and out-of-order messages. | Retain stable message and entity identifiers. | No duplicate operational action; stale updates are identified. |  |  | Not run
UAT07 | INT05 | Provide conflicting vessel or call identifiers. | Prepare two disagreeing source records. | Conflict remains visible and reaches its designated owner. |  |  | Not run
UAT08 | INT08 | Stop a live feed during an active workflow. | Record expected freshness thresholds and fallback procedure. | Operator sees source loss and can follow approved degraded operation. |  |  | Not run
UAT09 | ACC02 | Restore the feed after authorized manual entry. | Retain manual entries and replayed source records. | Recovery reconciles records without erasing manual decisions. |  |  | Not run
UAT10 | GOV01 | Attempt actions outside the account role. | Test viewing, proposing, approving and configuring separately. | Unauthorized actions fail and required audit evidence is retained. |  |  | Not run
UAT11 | GOV02 | Change a rule or privileged setting. | Use an authorized account and approved change. | Audit retains prior value, new value, actor and reason. |  |  | Not run
UAT12 | OPS07 | Review a boundary change and stale position. | Use approved coordinate reference and boundary versions. | Map and non-map views expose the relevant restriction and source age. |  |  | Not run
UAT13 | OPS08 | Reconcile a report for a sample period. | Freeze state definitions and sample-call population. | Totals trace to records with explained exclusions. |  |  | Not run
UAT14 | ACC03 | Run agreed load and concurrency conditions. | Record dataset, infrastructure and measurement window. | Measured response and recovery satisfy port-approved targets. |  |  | Not run
UAT15 | ACC04 | Complete key tasks using only a keyboard. | Use the agreed browser and target screen size. | Controls have visible focus and tasks can be completed. |  |  | Not run
UAT16 | ACC05 | Reconcile migrated records and exercise rollback. | Agree counts, key-field checks and rollback trigger. | Exceptions are assigned and rollback restores the agreed state. |  |  | Not run
UAT17 | GOV05 | Restore a backup into an isolated environment. | Agree restore point and recovery objectives. | Recovered data and elapsed time meet documented criteria. |  |  | Not run
UAT18 | ACC06 | Review operational readiness with each owner. | Include training, support, defects and rollback evidence. | Authorized sign-off records remaining conditions and owners. |  |  | Not run

## Defects and release
Defects and release decisions
Critical defects block sign-off; a major exception needs an authorized owner, workaround and dated resolution. Source: B13.
Defect ID | Test ID | Severity | Operational impact | Workaround | Owner | Due date | Retest evidence | Disposition

## Release readiness
Release readiness
An authorized port owner records the final decision after evidence is reviewed.
Readiness item | Required evidence | Owner | Evidence reference | Decision | Conditions or date
Critical defects closed |  |  |  | Pending
Major exceptions accepted with dates |  |  |  | Pending
Migration reconciled |  |  |  | Pending
Training complete for each shift |  |  |  | Pending
Support and escalation active |  |  |  | Pending
Rollback position confirmed |  |  |  | Pending
Restore and continuity tested |  |  |  | Pending
Final acceptance authorized |  |  |  | Pending